## SITREP Data
Date | Status | Mission # | Base MSN # | Aircraft # | Scheduled Launch | Launch Time | Recovery Time | Hours | Tach Time | Hover Time | Manual Control | Payload 1 | Payload 2 | Payload 3 | REASON for Cancel, Abort or Delay | Weather | Winds | OAT | Risk Level | Reason for Elevated Risk | TOIs | Notes | Staging
2021-08-05 | Complete | 20251116_01 | 20251116_VB | 200079 | 44413.4722 | 11:20 | 12:04 | 0.73 | 1.1 | 0.1 | No | Dummy | Comms Relay-123 |  |  | Weather - Clear | 070/11 | 33 | Low |  | 0 |  | Date | Status | Mission # | Base MSN # | Aircraft # | Scheduled Launch | Launch Time | Recovery Time | Hours | Tach Time | Hover Time | Manual Control | Payload 1 | Payload 2 | Payload 3 | REASON for Cancel, Abort or Delay | Weather | Winds | OAT | Risk Level | Reason for Elevated Risk | Fuel In (Actual) | Fuel Out (Actual) | Fuel Burn | TOIs | Notes
2021-08-06 | Complete |  |  | 200080 | 8:10 | 8:10 | 9:30 | 1.33 | 1.4 | 0.1 | No | Dummy | Comms Relay-123 |  |  | Weather - Clear | 058/17 | 26 | Low |  |  |  | 44545 | Complete | 20251216_VB080_01 | 20251216_VB080 | 200080 | 13:00 | 14:00 | 15:00 | 0 | 0 | 0 | 0 | MWIR 3.6-960202 | 0 | 0 | 0 | 0 | 360@10 | 25 | High | 0 | 0 | 0 | 0 | 0 | 0
2021-08-06 | Complete |  |  | 200079 | 12:30 | 12:30 | 15:00 | 2.5 | 3 | 0.1 | No | Other | Comms Relay-123 |  |  | Weather - Clear | 258/8 | 26.6 | Low
2021-09-14 | Complete |  |  | 200085 | 14:57 | 14:57 | 18:46 | 3.82 | 4.1 | 0.1 | No | EO950 | Comms Relay-123 |  |  | Weather - Clear | 305@22kts | 32 | Low |  |  | unscheduled flight
2021-09-15 | Complete |  |  | 200085 | 12:00 | 12:25 | 19:19 | 6.9 | 7.1 | 0.1 | No | EO950 | Comms Relay-123 |  | Delay - Ship - Other | Weather - Clear | 272@22kts | 32 | Low
2021-09-21 | CNX |  |  | 200080 | 0:00 |  |  | 0 | [6 empty] | Cancelled - Weather - Rain | Weather - Rain | 330@14kts | 26 | Low
2021-09-22 | CNX |  |  | 200080 | 20:00 |  |  | 0 | [6 empty] | Cancelled - Weather - Low Ceiling | Weather - Low Ceiling | 330@18kts | 28 | Low
2021-09-23 | CNX |  |  | 200080 | 0:00 |  |  | 0 | [6 empty] | Cancelled - Weather - Low Ceiling | Weather - Low Ceiling
2021-09-24 | Delay |  |  | 200080 | 0:00 |  |  | 0 | [6 empty] | Delay - Back Up AV Used | [6 empty] | Launch cancelled launch button/launcher issues
2021-09-24 | Delay |  |  | 200079 |  | 7:50 | 14:17 | 6.45 | 6.8 | 0.1 | No | EO950 | Comms Relay-123 |  | Delay - Ground Equipment | Weather - Low Ceiling | 030@10kts | 30 | Low |  |  | Unscheduled flight after night cancelled
2021-09-25 | Complete |  |  | 200080 |  | 19:07 | 23:41 | 4.57 | 4.8 | 0.1 | No | EO960 | Comms Relay-123 |  |  | Weather - Rain - Light | 335@10kts | 28 | Low |  |  | unscheduled flight
2021-09-26 | Delay |  |  | 200080 | 19:00 | 19:30 | 23:34 | 4.07 | 4.2 | 0.1 | No | EO960 | Comms Relay-123 |  | Delay - Weather - Rain | Weather - Rain - Light | 322@12 | 30 | Low |  |  | Delayed due to rain ship sped away from shower launched soon after
2021-09-28 | Delay |  |  | 200080 | 4:00 | 4:37 | 11:54 | 7.28 | 7.5 | 0.1 | No | EO960 | Comms Relay-123 |  | Delay - Ground Equipment | Weather - Rain - Light | 145@11 | 28 | Low |  |  | Delayed to to launch pad not connecting/switch pad out and launched
2021-09-29 | Delay |  |  | 200080 | 10:00 | 10:35 | 15:33 | 4.97 | 5.2 | 0.1 | No | EO960 | Comms Relay-123 |  | Delay - Weather - Rain - Heavy | Weather - Rain - Light | 340@12 | 29 | Low |  |  | Delayed due to heavy rain as soon as passed launched aircraft
2021-09-29 | Complete |  |  | 200079 |  | 14:37 | 18:30 | 3.88 | 4.1 | 0.1 | No | EO950 | Comms Relay-123 |  |  | Weather - Clear | 320@6 | 23.9 | Low |  |  | relief on station aircraft.
2021-10-01 | Delay |  |  | 200080 | 13:00 | 13:30 | 21:20 | 7.83 | 8 | 0.1 | No | EO960 | Comms Relay-123 |  | Delay - Weather - Winds - Gusting | Weather - Wind | 287@13 | 28.5 | Low |  |  | Delayed due to winds exceeding 25kts and gust up to 30kts
2021-10-03 | CNX |  |  | 200080 | 17:00 | 17:05 | 17:06 | 0.02 | 0.2 | 0.1 | No | EO960 | Comms Relay-123 |  | Cancelled - Equipment Failure |  | 198@17 | 28.2 | Low |  |  | Aircraft mishap in flight. Lost at sea.
2021-10-04 | Delay |  |  | 200079 | 13:00 | 13:50 | 19:10 | 5.33 | 5.5 | 0.1 | No | EO950 | Comms Relay-123 |  | Delay - Engine | Weather - Wind | 225@18 | 29 | Low |  |  | Delayed becouse of above aircrat.
2021-10-05 | CNX |  |  | 200085 | 7:00 |  |  | 0 | [6 empty] | Cancelled - Equipment Failure | [6 empty] | Midwing red on enunciation panel during engine run
2021-10-06 | Complete |  |  | 200079 |  | 7:45 | 15:31 | 7.77 | 8 | 0.1 | No | EO950 | Comms Relay-123 |  |  | Weather - Clear | 066@10 | 28.3 | Low |  |  | After repairs was verified launched to support TOI mission. V-BAT200079 launched for a successful mission event (7.8 hrs). Experienced severe comms degradation at 20-23nm from ship. Multiple loss comms routes were executed until ship was in the <25nm range. Working through the issues in flight, TOI was still located and tracked via V-BAT200079. 1 TOI, 3 people, 2338KG seized. Currently troubleshooting comms issues. Starlink troubleshooting was successful, and V-BAT200079 files have been sent back for analysis.
2021-10-07 | Complete |  |  | 200079 |  | 17:55 | 22:45 | 4.83 | 5.3 | 0.1 | No | EO950 | Comms Relay-123 |  |  | Weather - Clear | 265@8 | 28 | Low |  |  | unscheduled mission to support TOI
2021-10-08 | Complete |  |  | 200079 |  | 5:08 | 10:24 | 5.27 | 5.5 | 0.1 | No | EO950 | Comms Relay-123 |  |  | Weather - Clear | 300@13 | 29 | Low |  |  | unscheduled mission to support TOI
2021-10-10 | Complete |  |  | 200079 |  | 13:07 | 18:40 | 5.55 | 5.7 | 0.1 | No | EO950 | Comms Relay-123 |  |  | Weather - Clear | 252@12 | 29.2 | Low |  |  | unscheduled mission to support TOI
2021-10-14 | CNX |  |  | 200079 |  |  |  | 0 | [6 empty] | Cancelled - Weather - Lightning | Weather - Lightning | [5 empty] | delayed for rain/low ceilings and finally cancelled due to lightning/thunderstorms on station
2021-10-15 | CNX |  |  | 200079 | 18:00 |  |  | 0 | [6 empty] | Cancelled - Weather - Rain - Heavy | Weather - Rain - Heavy | [5 empty] | Cancelled due to heavy rain and low ceilings
2021-10-21 | Complete |  |  | 200079 | 21:00 | 19:10 | 1:34 | 6.4 | 6.7 | 0.1 | No | EO960 | Comms Relay-123 |  |  | Weather - Winds - Gusting | 330@22 | 30 | Low |  |  | Launched early for mission support
2021-10-23 | Delay |  |  | 200079 | 4:00 | 5:10 | 11:42 | 6.53 | 6.7 | 0.1 | No | EO960 | Comms Relay-123 |  | Delay - Camera Replaced | Weather - Low Ceiling | 344@19 | 21 | Low |  |  | delayed launch for camera issues poor weather conditions had to land early
2021-10-23 | CNX |  |  | 200085 |  | 16:03 | 16:03 | 0 | 0.1 | [5 empty] | Cancelled - Equipment Failure | [6 empty] | Aircraft came off launcher during engine run tipping over. Loss of aircraft
2021-10-25 | CNX |  |  | 200079 | 20:00 |  |  | 0 | [6 empty] | Cancelled - Engine | [6 empty] | Flight with V-BAT200079 was scheduled for 2000L. After engine runs and high power, pitch and roll of the ship visually looked more drastic than what crew was used to. V-BAT200079 had significant movement inside the launcher and looked very unstable as called out by the AO/AV during engine runs. Multiple checks with the ship confirmed our max limits for both pitch and roll. The entire evolution was halted and a discussion amongst the crew utilizing ORM and sound judgement was conducted. Engine was shut down as ship adjusted course for safety. After a second preflight, V-BAT200079 would not achieve the minimum 6850 RPM during max power checks. Three separate high-power runs were performed on the flight deck with each one failing RPM checks by a significant amount. Engine was shut down and moved in hangar for troubleshooting. Both Injectors, and new vaporizer have been installed.
2021-10-27 | Delay |  |  | 200079 | 16:00 | 16:56 | 22:23 | 5.45 | 5.8 | 0.1 | No | EO960 | Comms Relay-123 |  | Delay - Ship - Other | Weather - Low Ceiling | 040@16 | 23.6 | Low |  |  | Delayed due to ship speed/manuever around another vessel before restarting preflight for tracking ins. Flight with V-BAT200079 at 1600L (5.5hrs). Investigated ships radar contacts with no suspicious or unusual activity found. Upon landing in 9kt winds, V-BAT200079 overshot the landing pad by approximately 15 feet. V-BAT200079 then stabilized and overflew the pad in the opposite direction and landed 6 feet away from the pad. Reaching out to fleet support for guidance on this issue.
2021-10-30 | Complete |  |  | 200079 | 21:00 | 19:05 | 22:15 | 3.17 | 3.5 | 0.1 | No | EO960 | Comms Relay-123 |  |  | Weather - Low Ceiling | 345@17 | 23 | Low |  |  | Launched early for mission support
2021-10-31 | Complete |  |  | 200079 |  | 10:10 | 14:02 | 3.87 | 3.9 | 0.1 | No | EO960 | Comms Relay-123 |  |  | Weather - Low Ceiling | 290@16 | 22 | Low |  |  | unscheduled flight to support mission
2021-11-03 | Complete |  |  | 200079 |  | 15:54 | 22:19 | 6.42 | 6.5 | 0.1 | No | EO960 | Comms Relay-123 |  |  | Weather - Clear | 310@12 | 24 | Low |  |  | unscheduled mission to support TOI
2021-11-04 | Delay |  |  | 200079 | 16:00 | 16:25 | 20:37 | 4.2 | 4.3 | 0.1 | No | EO960 | Comms Relay-123 |  | Delay - Ship - Other | Weather - Low Ceiling | 160@15 | 25 | Low |  |  | unscheduled mission to support TOI
Formulas:
Date = IF(sitrep_Data[[#This Row],[Date]]="","",sitrep_Data[[#This Row],[Date]])